## Sheet1
FDP Form 6 - Trust Fund Utilization
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS or ACTIVITIES
FOR THE 1st QUARTER, CY 2015
Province, City or Municipality: LAOAG CITY, ILOCOS NORTE
Program or |  |  |  | Target | Project Status |  | No. of
Project |  |  |  | Completion | % of | Total Cost | Extensions, if
| Location | Total Cost | Date Started | Date | Completion | Incurred to Date | any | Remarks
a. Health Services/Medical Assiss- | Laoag City, Ilocos Norte | 2213750 | 2011 |  |  | 403558 |  | On-going
tance | [7 empty] | Bal.-P1,810192.00
b. Social Services | Laoag City, Ilocos Norte | 3600823 | 12/2014 |  |  | 44913 |  | On-going
c. Sports Development | Laoag City, Ilocos Norte | 233780 | 12/2014 |  |  | 38000 |  | Bal.-P195,780.00
PDAF of Sen. Antonio F. Trillanes IV |  | 500000 | 2013-06-21
a. Financial Assistance | Laoag City, Ilocos Norte |  | 10/2014-12/2014 |  |  | 10000 |  | Bal.- P490,000.00
DPWH-Maintenance of Local Road Fund | 50% | 2011042 | 2014
| 50% | 2011042 | 2014
Concrete ReblockingMaintenance & | San Mateo-Lataag Bacsil Rd. |  | 2014-12-18 |  |  | 3637098 |  | Implemented
Repair of Infra-Facilities | Laoag City | [6 empty] | Bal.-10% Retention
| Cavit-Gabu Norte Road |  | 2/8/2014 |  |  |  |  | P384,986.00
DILG-Performance Challege Fund-Rehabi-
litation/Improvement Works |  | 3000000 | 2014
Construction of Slope Protection, | Brgy. 54-A Lagui-Sail, Laoag
Drainage & Leache Pond at Sanitary |  |  | 2014-11-15 |  |  | 2706608.11 |  | Completed
Landfill | [7 empty] | Bal- 10% Retention
293391.89
DSWD-Ro I-Supplemental Feeding Program | Laoag City | 3900000 | 2014-07-10
Bal.-P1,950.00.00
N F A Rice |  |  | 12/2/2014 |  |  | 450000 |  | Implemented
Payment of goods |  |  | 12/8/2014 |  |  | 1500000
DOLE-Livelihood Starter Kit Project | Laoag City | 285000 | 2014-07-31
Elecl. Installation materials-8" long | [5 empty] | 284875 |  | Ret. Under O.R. No.
nose, 14 sets venier caliper, &
19 pcs. Mattress for beuaty care | [7 empty] | P125.00
body massage
Early Childhood Care & Development |  |  | 2014-03-24
Council-ECCDC |  | 2300000 | [5 empty] | On going
Construction of National Children | Brgy. 2 Laoag City |  | 12/2014 |  |  | 1480784.39 |  | Bal.-P819,208.03
Development Center Building
DPWH-Dept. of Agrarian Reform-Mainte- |  |  | 2014
nance of Infrastructure Facilities |  | 4240000
Concreting of Farm to Market Roads | Balacad, Laoag City |  |  |  |  | 1192839.85 |  | Completed
| Lataag, Laoag City |  | 2014-12-29 |  |  | 1484957.38 |  | Completed
| Lagui-Sail, Laoag City |  |  |  |  | 1562202.77 |  | Completed
We hereby certify that we have reviewed the contents and hereby attest to
the veracity and correctness of the data or information contained in this
document.
____________________________
_____________________________ | [5 empty] | CHEVYLLE V. FARIÑAS
ELENA V. ASUNCION | [5 empty] | City Mayor
City Treasurer

## Sheet2
FDP Form 6 - Trust Fund Utilization
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS or ACTIVITIES
FOR THE 2nd QUARTER 2021
Province, City or Municipality: LAOAG CITY, ILOCOS NORTE
Program or |  |  |  | Target | Project Status |  | No. of
Project |  |  |  | Completion | % of | Total Cost | Extensions, if
| Location | Total Cost | Date Started | Date | Completion | Incurred to Date | any | Remarks
1. PDAF OF Cong. Rodolfo C. Fariñas
Financial Assistance | Laoag City & 1st | P 45,535,000.00 | Feb. 2011 to |  |  |  |  | Balance-P 1,331,943.44
| District of Ilocos |  | present
a. Health/Social Services | Norte |  |  |  |  | 8420443
b. Sports Development | [5 empty] | 1144998
c. Livelihood Program | [5 empty] | 75000
d. Subsidy to Local Govt. Units | [5 empty] | 18935610.51
e. Infrastructure Projects-Repair/Construction/ | [5 empty] | 15627005.05
Improvement/Rehabilitation of School buildings,
multipurpose buildings, concrete pavement,
farm to market roads, drainage system &
slope protection
Total | [5 empty] | 44203056.56
2. Dept. of Agriculture-Cash Prize for |  | P 1,000,000.00 | Feb. 2015 |  |  |  |  | Bal.-P 38,285.00
National Quality Corn Achievers Award | [7 empty] | On going
Cash Prize for National Corn Achievers Award |  | P 2,000,000.00 | Dec. 03, 2015
IT Supplies use at Agriculture Office | [5 empty] | 99900
25 units motor pump | Diff. barangays of Laoag |  |  |  |  | 395000
70 bags Dekalb RR-BT | Diff. barangays of Laoag |  |  |  |  | 454815
13 units 5HP Air-cooled diesel engine | [5 empty] | 216580
396 bags Organic Fertilizers | [5 empty] | 948620
1 unit L-300 De Luxe | [5 empty] | 785500
3 units 5HP Air-cooled diesel engine | [5 empty] | 49300
Adjustmment | [5 empty] | 12000
Total | [5 empty] | 2961715
3. LGSF- Local Government Support Fund | 48-A Cabungaan L.C. | 14592816 | April 16,2020 |  | 100% |  |  | Balance- 0
Establishment of Forest Park | [7 empty] | Implemented
REMAR CONSTRUCTION | [5 empty] | 14592816
Program or |  |  |  | Target | Project Status |  | No. of
Project |  |  |  | Completion | % of | Total Cost | Extensions, if
| Location | Total Cost | Date Started | Date | Completion | Incurred to Date | any | Remarks
4. Dept. of Agriculture-BUB-CY 2015 | City Agriculture Office | P 603,000.00 | Nov. 4, 2015 |  |  |  |  | Balance P 59,496.86
Vermiculture & Composting-90% | Laoag City | [6 empty] | Under Implementation
of the Improvement & Expansion of
Bodega for the Implementation of
various projects
Payment of Stock House, Ver House W/ 3 beds | [5 empty] | 291400
Payment of Shredder Chipper Machine | [5 empty] | 130000
Payment of Tea brewer | [5 empty] | 27000
Expenses | [5 empty] | 30000
Payment of honorarium Arlene Gaoiran | [5 empty] | 2480.87
honorarium Arlene Gaoiran, March 2017 | [5 empty] | 5000
honorarium Arlene Gaoiran, April 2017 | [5 empty] | 5000
honorarium Arlene Gaoiran, May 2017 | [5 empty] | 5000
honorarium Arlene Gaoiran, June 2017 | [5 empty] | 5000
Adjustment | [5 empty] | 360
honorarium Arlene Gaoiran, August 2017 | [5 empty] | 7366.82
honorarium Arlene Gaoiran, Sept .& October 2017 | [5 empty] | 20549.54
honorarium Arlene Gaoiran, Nov. 2017 | [5 empty] | 8530
honorarium Arlene Gaoiran, Dec. 2017 | [5 empty] | 5815.91
total | [5 empty] | 543503.14
5. DOH- ROI -HOSPITAL FACILITY ENHANCEMENT PROGRAM | LCGH | 70000000 | [5 empty] | Balance 9,000
| Brgy. 46 Nalbo L.C. | [6 empty] | completed
Low Temperature Plasma Free Sterilizer |  |  |  |  | 100% | 7998000
C- Arm Fluoroscopy Machine | [5 empty] | 13498000
Endoscopy Machine with Gastroscope,Colonoscope & Bronchoscope | [5 empty] | 13199000
Mechanical Ventilator | [5 empty] | 10296000
Medical Oxygen Generating Machine | [5 empty] | 25000000
Total | [5 empty] | 69991000
Program or |  |  |  | Target | Project Status |  | No. of
Project |  |  |  | Completion | % of | Total Cost | Extensions, if
| Location | Total Cost | Date Started | Date | Completion | Incurred to Date | any | Remarks
6. DSWD -Field Office I | Laog City | 4680000 | 2018-06-01 |  |  |  |  | Balance - 860.00
Supplemental Feeding Program | [7 empty] | completed
NFA Rice |  |  |  |  | 100% | 936000
Payment of goods | [5 empty] | 1474000
Payment of goods | [5 empty] | 397220
Payment of goods | [5 empty] | 397220
Payment of goods | [5 empty] | 1474700
Total | [5 empty] | 4679140
7. Dept. of Agriculture- RFOI
Cattle Feedlot Fattening Project under RA 11469 "Bayanihan | Laoag City | 5000000 | 2021-03-01 |  |  |  |  | Balance 5,000,000
To Recover as one"
8. Department of Agriculture | Laoag City | 119400 | 2018-07-01 |  | 100% |  |  | Balance 1,053.5
Implementation of Demo Farms and Training Center on
Organic Vegetables
Payment of 2 caracow- St. Ruiz Agro Farm Supply | [5 empty] | 69000
Payment of 4 packs Eggplant Seeds- St. Ruiz Agro Farm Supply | [5 empty] | 49346.5
Total | [5 empty] | 118346.5
9. Bureau of Treasury
Purchase of 82 units Multicab |  | 24236000 |  |  | 100% | 24236000 |  | Balance- 0
Improvement of 90 Sport Facilities (Basketball Courts) | Laoag City | 3960000
Payment of fiberglass basketball board |  |  |  |  | 100% | 3933000 |  | Balance- 27,000.00
returned to BOT
10. Department of Environment and Natural Resources | 54-A Lagui | 1771403 | [5 empty] | Balance- 0
EMV - For Closure and Rehabilitation of Controlled | Laoag City
Dumpsite
ZEDIC BUILDERS | [5 empty] | 1760000
UNEXPENDED AMOUNT REFUNDED TO DENR | [5 empty] | 11403
1771403
Program or |  |  |  | Target | Project Status |  | No. of
Project |  |  |  | Completion | % of | Total Cost | Extensions, if
| Location | Total Cost | Date Started | Date | Completion | Incurred to Date | any | Remarks
11. DILG-CBMS | Laoag City | 1000000 | September 2016 |  |  |  |  | Balance 174,771.00
| LGU counterpart | 1425356 | [5 empty] | Completed
| total | 2425356
IT Equipment for the CBMS Database | [5 empty] | 48000
Tablets for CBMS survey/data gathering | [5 empty] | 608826
Training Kits for CBMS | [5 empty] | 14800
Honorarium of Sonny Arnold Pascual | [5 empty] | 12000
Meals & snacks CBMS Module 1 training | [5 empty] | 112500
Honorarium to CBMS Enumerators | [5 empty] | 220680
Honorarium Danielle Dapne Abadilla et al | [5 empty] | 235165
Honorarium Maria Mica Adera et al | [5 empty] | 197718
Honorarium Maria Mica Adera et al | [5 empty] | 148672
Honorarium Maria Mica Adera et al | [5 empty] | 83105
Honorarium Maria Mica Adera et al | [5 empty] | 74855
Honorarium Maria Mica Adera et al | [5 empty] | 96085
Honorarium of CBMS Trainors | [5 empty] | 12000
Meals & snacks CBMS Module 2 training | [5 empty] | 15000
Snacks of CBMS Validation | [5 empty] | 32000
Meals and Snacks of CBMS module training | [5 empty] | 254000
Meals and Snacks of CBMS module training | [5 empty] | 25600
Honorarium for trainors Module 3 | [5 empty] | 12000
Module 3 training kits | [5 empty] | 19154
Honorarium for CBMS Trainors | [5 empty] | 4800
Module 4 training kits | [5 empty] | 23625
TOTAL | [5 empty] | 2250585
We hereby certify that we have reviewed the contents and hereby attest to
the veracity and correctness of the data or information contained in this
document.
ARTURO DIOMEDES B. GAYBAN |  |  |  |  | MICHAEL MARCOS KEON
City Treasurer | [5 empty] | City Mayor

## Sheet3
DSWD E-AICS
FINANCIAL ASSISTANCE
SURGICAL/DIALYSIS
DOH | DOH